Black Hawk County Multi-Jurisdictional Hazard Mitigation Plan Update

Schedule of Committee Meetings

| Meeting | Date | Agenda Items and Tasks |
| --- | --- | --- |
| #1 | Jan 22, 2026 | Agenda Items - Overview of What to Expect - Purpose of a Multi-Jurisdictional Approach - Local Disaster Management: Hazard Mitigation - Assessing Hazards and Risk – Hazard Profiles and History Resources to Know - Local Mitigation Planning Policy Guide (Appendix A: Review Tool) Tasks - Community Profile Worksheet - 2020 Action Plan Update Responses - Local Hazard Risk Assessment - Vulnerability Assessment |
| #2 | Feb 19, 2026 | Agenda Items - Review Hazard Assessment Results - Capability Assessment and NFIP - Mitigation Action Selection Tasks - Capability Assessment - National Flood Insurance Program Assessment - Problem Statements –Building Hazard Mitigation Action Strategies - Mitigation Action Selection and Implementation |
| #3 | March 19, 2026 | Agenda Items - Review Uncompleted Items - Plan Update Evaluation - Individual Community Meetings, as needed |
| Next Steps | April and May 2026 | Tasks - Review and Finalize Draft Plan - Adoption |

| # | Tasks | Date | Description |
| --- | --- | --- | --- |
| 1 | INRCOG will finalize local plan draft and post online for public comment period. Participants will need to review as needed. | April 2026 | Each participating jurisdiction will have a draft of a local hazard mitigation plan developed for them that meets requirements for approval by FEMA Drafts of each plan will be posted online for 7-day public comment period (INRCOG). Review grammar, names, titles. Format if needed to your city templates if needed. Add a few pics, etc. Limit moving around content, in order pass state and federal review. |
| 2 | Share with your city leaders/boards and hold a public hearing for comments, input by community at city council/school district meeting. Publish notice in the paper between 4-20 days prior to the board meeting. | May 2026 | Confirm council/board meeting dates and location with Isaiah. Boards will approval plan with resolution provided by INRCOG. |
| 3 | INRCOG will submit the county MJ-HMP to Black Hawk County Board of Supervisors for approval and adoption of resolution. | May 2026 | Update plans to include resolutions and public feedback. |
| 4 | INRCOG: Prepare and submit entire plan for 1st review by state mitigation office (Iowa Homeland Security). | June 2026 | 45-day review period. Make any necessary changes from review. |
| 5 | Iowa Homeland Security will submit the reviewed plan for FEMA review. | July 2026 | 60-day review period. |
| 6 | Plan is APPROVED and Jurisdictions are eligible for FEMA program funds until 2030. | September 2026 | Get FEMA approval letter. See you in 5 years! |